## Sheet1
SL.NO | MODULE |  | COMMENT | ACTION
| HCM Report | Qc.No |  |  | Programmer
1 | Visa Bundle Report | 1
|  |  | 9.Provide menu icon |  | Not Closed
|  |  | 12.Change the design of page of first labels. |  | Not Closed
| On-Boarding Status report |  | Upnormality after printng.Printing Results will displaying on main page. |  | Closed
|  |  | Icon not displaying in menu and page. |  | Not Closed
Inner page
|  |  | Change the design of the page |  | Closed
|  |  | The Candidate name should be displayed in only one line.(some names are diplaying in like an upnormality. |  | Not Closed
| Employee Details Report |  | Provide the menu icon |  | Not Closed
|  |  | Age from to should be calibri font. |  | Not Closed
|  |  | The dropdowns should be in autocompletion(in filter options)Divisons,Project |  | Not Closed
|  |  | Abnormality in print page.Prining values different from the page. |  | Not Closed
2 | Inner Page
|  |  | while printing the divisions name duplicating |  | Not Closed
|  |  | Employee name is not displaying in print page |  | Not Closed
| Employee Recruitment Report |  | Provide the menu icon and page icon.
|  |  | Allign the filter box properly.It will overhiding the another page section. |  | Not Closed
|  |  | Year DDL should be in an autocomplteion |  | Not Closed
|  |  | Only display the confirmed candidate in joining intimation.Remove the rejcted candidate details from the list. |  | Not Closed
| Inner Page |  | Upnormality in status columns from the list table. |  | Not Closed
|  |  | Table scroll is not working in list table. |  | Not Closed
|  |  | Allign the print button properly. |  | Not Closed
|  |  | Rename the more details to more info |  | Not Closed
|  |  | Upnormal values are displaying in lists.(Same values displaying in different months) |  | Not Closed
| ManPower Recuirement status report |  | Status should be in Upper cases. |  | Not Closed
3 |  |  | Rename the division manager approved to REQUEST APPROVED |  | Not Closed
|  |  | Requst rejected status is missing in report page. |  | Not Closed
|  |  | Provide menu and page icon |  | Not Closed
|  |  | Department DDL SELECT ITEMS should be in order first/Default |  | Not Closed
|  |  | Make proper values in referance columns |  | Not Closed
|  |  | Change the design of print in candidate details section. |  | Not Closed
4
5
6
7
8
9
10
11
12