## Planner
SL# | JOB DETAILS | TARGET DATE AND TIME | TEAM MEMBER
SPRINT - 4
1 | SALES PRINT | 12-02-2016 06.30PM | EVM-0002
| INSTALLATION DATE | 2016-02-15
2 | MODIFICATION ON RETURN,OPENINGSTK,PRODUCTION,LABEL GENERATION | 11-02-2016 12.30PM | EVM-0003
3 | INVOICE PRINT TRACKING | 12-02-2016 12.30PM | EVM-0003
3 | SALES DOCUMENT DETAILS MODULE | 17-02-2016 12.30PM | EVM-0003
4 | EXPORT PRINT SUB SYSTEM ( NEW MODULE ) | 25-02-2016 12.01PM | EVM-0003
5 | NEW PRINT FOR EXPORT | 26-02-2016 06.00PM | EVM-0003
| INSTALLATION DATE | 2016-02-29
SPRINT - 5
6 | INVOICE DELIVERY STATUS MODULE | 29-02-2016 06.00PM | EVM-0003
7 | PACKING LIST | 02-03-2016 12.01PM | EVM-0003
8 | REPORTS | 07-03-2016 06.00PM | EVM-0003
1.SALES ORDER REPORT
2.INVOICE PRINT DETAILS REPORT
3.INVOICE DOCUMENT STATUS REPORT
4.STOCK REGISTER REPORT - MODIFICATION
5.ITEM LISTING REPORT - MODIFICATION
6.SUPPLEMENTARY COST REPORT
7.COMMODITY CODE SALES REPORT
9 | SALES RETURN PRINT MODIFICATION | 08-03-2016 11.00PM | EVM-0003
10 | DISCOUNT ALLOCATION MODULE | 09-03-2016 06.00PM | EVM-0003
| INSTALLATION DATE | 2016-03-11